## Slide 1: Potential Scenic Sites Analysis for the Hill Country Conservancy
Nancy A. Heger, Manager Gene Sipes, Assistant Manager
Matt Broadaway, GIS Analyst Matt Gray, Web Master
Image source: http://www.philadelphianstours.com/

## Slide 2: Progress Report
Brief Project Description
Past Work
Current Work
Work Completed
Future Work
Final Deliverables
Conclusions

## Slide 3: Purpose
Identify potential sites for future preservation by the Hill Country Conservancy (HCC)
Identify areas that are “scenic” as defined by factors such as topographical relief, proximity to water bodies, and vegetation.
Provide a map of potential scenic sites that HCC can use to identify areas for future preservation
SCOPE
Study region - 22 county area in
Hill Country
Will take approximately 3 months
(6 Sept. to 13 Dec.)

## Slide 4: Past Work - Model Criteria
Road Buffer
  3 mile buffer around roads
Topographic Variation i.e. slope
  Areas with more relief preferred
Distance from streams
  Areas closest to streams preferred
Distance from State Parks/Historic Sites
  Areas closest to State Parks preferred
Distance from unique natural feature
e.g. Enchanted Rock
  Areas near these features preferred
Land Use
  Areas with preferred vegetation types

## Slide 5: Current Work
Current Model Criteria:
  Distance from streams
    Areas closest to streams preferred
  Land Use
    Omit all urban areas
  Topographic Variation i.e. slope
    Areas with more relief preferred
Reassessment of current suitability model and viewshed analysis
Testing of revised model and refinement of viewshed analysis

## Slide 6: Work Completed
Data collection and preparation
Pilot study run on Hays County using scenic suitability model
Viewshed Tests

## Slide 7: Hays County Pilot Study
Model needs refinement
  Scoring changes
  Weighting
  Variables used

## Slide 8: Creation of Tools to View Results
Toolbar demo

## Slide 9: Creation of Tools to View Results

## Slide 10: Viewshed Tests by County

## Slide 11: Viewshed From Rivers

## Slide 12: Future Work
Use visualization tools to validate model
Refine model and scoring system
Mosaic county viewsheds and run model on viewable area
Use Arc Scene - ESRI product that allows 3-D visualization

## Slide 13: Arc Scene

## Slide 14: Final Deliverables
Final deliverables will include:
A Detailed Final Report (2 copies)
Professional Poster for display in the Geography Department
Website
CD (2 copies) containing
  All data
  Metadata
  Proposal, Progress, and Final reports
  Poster
  Power Point presentation
  Instructions on how to use CD (readme file)

## Slide 15: Conclusions
Need model refinement
  In the process of revising model scoring, weighting, and criteria used to identify scenic areas
Model validation
  Once model is refined, it will be validated using SyncArcGE tool
Viewshed analysis on a smaller scale may be do-able
  Currently running county viewsheds, which will be combined to access scenic value of viewable areas.
Other potential viewing
  Arc Scene
Outcome
  Model will be created that can be used in other areas to determine scenic beauty.