## Slide 1: 10/31/2012 progress report
Prepared for the Texas Department of Transportation

## Slide 2: Subject
Brief synopsis
Examine the three deliverables
Plans for completion

## Slide 3: Purpose
Determine if the expansion of runways 13-31 and 17-35 is feasible and what impacts an expansion can have on the surrounding area of the San Marcos Airport.
Tasks:
  Investigate into expanding the lengths of runways 13-31 and 17-35 from existing length to ultimate length.
  Provide an airport hazard zoning map of imaginary surfaces.
  Provide a controlled compatibility land use map.

## Slide 4: Scope
The scope for this project is two-fold.
  Ground extent
  Air extent
Ground extent is established by TXDOT aerial image.
  Runway center line buffer zones
Air extent is a 50,000 foot zone from the end of each runway.

## Slide 5: Task #1 – Runway Extensions
Work Completed
  Extension calculations completed
  “FAA Compliant”
  Extensions based on planning map provided with RFP
    13-31 a 800 ft. extension
      Added to 31 end of runway
    17-35 a 1500 ft. extension
      Broken up into two sections
        (23 feet above railroad line)
        558 ft. added to 17 end of runway
        1000 ft. added to 35 end of runway

## Slide 6: Task #1 – Runway Extensions
Present Work
  Adjusting the approach polygons for each runway
  Processing elevation data
  Modeling approach surfaces from proposed runway extensions
Future Work
  Evaluate object penetration through surfaces

## Slide 7: Task #2 – Imaginary Surfaces
Work completed
  Calculations for approach angles and distances for 13-31 runway complete
Present work
  Calculating approach angles and distances for 17-35 runway
  Adjusting approach polygons to their proper z-values
Future work
  Profile view of approach surfaces
    3D rendering

## Slide 8: Runway Extensions 31 and 35

## Slide 9: Runway Extensions 17

## Slide 10: Task #3 – Controlled Compatibility Land Use
Work completed
  Data collection process
  75% of parcel data “reclassified”
  Record crossover
Present work
  Reclassification of parcel data to existing land use categories
  Analysis of digital imagery
Future Work
  Buffer runway centerlines
    Extract existing land use

## Slide 11: Task #3 – Controlled Compatibility Land Use

## Slide 12: Conclusion
The three primary goals are moving at a consistent pace
  Data collection complete for all three tasks
  Analysis and evaluation in progress
  Future work accounted for
Defined dates for future tasks
  Analysis completion by November 15, 2012
  Final deliverables complete by December 10, 2012
Geo-Air Consulting is confident of on-time completion of this project for the Texas Department of Transportation.

## Slide 13: Questions or Comments?