## Slide 1
San Marcos Municipal Airport Airspace Planning Project
Prepared for:
Texas Department of Transportation

## Slide 2: Our Team
Jason Ford: Project Manager / GIS Analyst
Patricia Michel: GIS Analyst
Grayson Jones: GIS Analyst
Casey Carpenter: GIS Analyst

## Slide 3: Contents
Introduction
  Purpose
  Scope
Project Tasks
  Task 1
  Task 2
  Task 3
Issues
Revised Timeline
Appendix: Figures
Questions

## Slide 4: Introduction
Project Start Date: September 30, 2013
Reminder of this planning study’s purpose and scope
Detailed information about the progress of this planning study
  Work completed, work in progress, work planned
Revised task list that breaks down the original tasks for more information
Revised timeline

## Slide 5: Purpose
Goal: Provide the city of San Marcos with the tools and information required to enact zoning regulations that will protect and preserve the air space surrounding the San Marcos Municipal Airport.
Task 1: To create an updated hazard-zone map for the San Marcos Municipal Airport
Task 2: Create specialized GIS layers and 3D visualization reference imagery
Task 3: Develop a user-friendly interactive screening tool using Manifold that can identify maximum allowable heights and current penetrations in imaginary surfaces.

## Slide 6: Scope
Geographic extent is centered on the San Marcos Municipal Airport
  Reference point is 29°53’34” N 97°51’47”
  Operational runways are 8/26, 13/31, and 17/35
Planning study extent is concerned with both ground and airspace of the surrounding areas
  Primarily concerned with all areas that fall within the zones that are created by the imaginary surfaces
  Also concerned with areas surrounding the zones created by the imaginary surfaces in reference to any future regulation
  Cities that may be affected or fall into the scope of this study are San Marcos, Martindale, Kyle, Wimberley, and Lockhart

## Slide 7: Task 1: Updated Hazard-Zone Map
Create an updated hazard-zone map for San Marcos Municipal Airport.
Work Completed:
Data collection completed for all tasks
  County, City, Street, Digital Elevation Models, National Flight Data Survey, and GIS Survey Data
Imaginary surfaces created in ArcMap and ArcScene (viewable in both 2D and 3D)
  Referenced Federal Aviation Administration Code of Federal Regulations 14 part 77 and AutoCAD line data

## Slide 8: Task 1 (cont.)
Work in Progress: Design the layout of the final deliverable hazard-zone map and creation

## Slide 9: Task 1 (cont.)
Imaginary Surfaces extruded in 3D
10x vertical exaggeration

## Slide 10: Task 2: Create specialized GIS layer and 3D Visualization
Work in Progress
  Create allowable height raster covering all imaginary surfaces
  Develop imaginary surface volumes for imaginary surfaces for 3D visualization purposes

## Slide 11: Task 2 (cont.)
Work Scheduled
  Create point class feature penetrations within imaginary surfaces
  Create point class feature identifying those obstructions in and around the airport hazard zones not penetrating imaginary surfaces

## Slide 12: Lowest Elevations of Imaginary Surfaces
10x vertical exaggeration

## Slide 13: Imaginary Surface Volumes
10x vertical exaggeration
Primary and Transitional Surfaces
Horizontal and Conical Surfaces

## Slide 14: Imaginary Surface Volumes (cont.)
10x vertical exaggeration
Approach Surfaces

## Slide 15: Task 3: Interactive Mapping Tool
Work Planned:
Decide the layout of the interactive screening tool. This will include design decisions regarding cartographic properties like color schemes, legend, scale, and labeling.
Determine which layers will be included in the interactive screening tool. Layers will be included based on their significance to the overall goal.
Determine overall tool functionality. This will include deciding how queries are made, zoom extent and functionality, layer transparency, and how layers will be toggled on and off.
Determine the method of displaying user queried information and error messages for invalid queries.

## Slide 16: Issues

## Slide 17: Issues
Surfaces are intersecting
and passing through each other
Proper shape after Merge,
Union and conversion
to Multipatch

## Slide 18: Issues
noticeable vertical walls and
plateaus instead of a consistent slope
Proper slope after converting to TIN

## Slide 19: Timetable
Oct
Nov
Dec
Start 30 Sep
Complete 9 Dec
4 Nov
25 Nov
2 Dec
Data Analysis ( 3 weeks )
Web and Map Development ( 3 weeks )
Data Interpretation ( 1 weeks )
Contingency ( 1 week )

## Slide 20: Conclusion
Ahead of schedule!
Work to be completed: Specialized GIS layers, configuring 3-D visualization, and developing our interactive mapping tool.
Confident to meet our deadline on December 9, 2013.

## Slide 21: Questions?