## Slide 1
San Marcos Municipal Airport Airspace Planning Project
Prepared for:
Texas Department of Transportation

## Slide 2: Our Team
Jason Ford: Project Manager / GIS Analyst
Patricia Michel: GIS Analyst
Grayson Jones: GIS Analyst
Casey Carpenter: GIS Analyst

## Slide 3: Contents
Introduction
  Background
  Purpose
  Scope
  Literature Review
Data and Software
Methodology
Implications
Budget
Timetable
Conclusion
Questions

## Slide 4: 1984 San Marcos Airport Hazard Zoning Map

## Slide 5: Background
Last hazard zoning map created in 1984
Increased growth and development
Increased airport usage
Regulations required to preserve airspace

## Slide 6: Purpose
To assist San Marcos enact hazard zoning regulations
Two primary goals
  Create 3D imaginary surfaces and hazard zoning map
  Create interactive screening tool

## Slide 7: Scope
Geographic extent is centered on the San Marcos Municipal Airport
Extent is concerned with both ground and airspace of the surrounding areas

## Slide 8: Scope cont.

## Slide 9: Literature Review
Past projects conducted for the New Braunfels Airport and San Marcos Airport
Title 14, Code of Federal Regulations, Part 77 - Safe, Efficient Use, and Preservation of the Navigable Airspace
Texas local government code Title 7 Subtitle C Chapter 241 – Municipal and County Zoning Authority around Airports
Airport Cooperative Research Program (ACRP) Report 38 – Understanding Airspace, Objects, and their effects on Airports

## Slide 10: Data
14 CFR 77 (e-Code of Federal Regulations)
DEM or NED (USGS)
Shapefiles for San Marcos Facilities (TxDOT)
Obstruction Point Data (TxDOT)
3D imaginary surfaces (produced in-house)
World Street Map (ESRI – reference only)
County Boundaries (TNRIS – reference only)

## Slide 11: Software
ArcScene and/or Google SketchUp
ArcGIS (for analysis and map creation)
Manifold (for web development)

## Slide 12: Analysis/Methodology:
Interactive Map content
Create an interactive map tool to be used by the City of San Marcos.
We will create 3D imaginary surfaces
Compare them with elevation models
Determine highest allowable building heights within each imaginary surface zone…

## Slide 13
Interactive Map content continued…
Our interactive map will contain a continuous layer of allowable heights even for areas where multiple zones overlap
Allow users to select any location on the map to find accurate maximum building height for that individual location.

## Slide 14
Obstructions Analysis:
Identify obstacles penetrating imaginary surfaces
Import obstruction point data and assign it appropriate elevation values (based on ground elevation and height of obstruction)
Compare obstruction elevation with elevation at same location on imaginary surface to determine if the obstruction is penetrating the surface and by how much

## Slide 15: Implications
Establish a new 2013 hazard-zoning map
Minimize encroachment
Possibility of increased economic traffic
Automated screening tool
Allowable heights
Obstructions penetrating through airspace

## Slide 16: Budget
Service Costs
Data Collection and Processing
$2,415
Data Analysis
$2,415
Web Development
$1,620
Map Development
$1,560

## Slide 17: Budget cont.
Equipment and Software Costs
Data Interpretation
$1,575
System Management
$1,600
Equipment Costs
$1,955.56
Software Costs
$2,050
Total $15,190.56

## Slide 18: Timetable
Oct
Nov
Dec
Start 30 Sep
Complete 6 Dec
7 Oct
21 Oct
11 Nov
2 Dec
Data Collection and Processing ( 3 weeks )
Data Analysis ( 3 weeks )
Web and Map Development ( 3 weeks )
Data Interpretation ( 1 week )

## Slide 19: Final Deliverables
Automated screening tool
Updated airport zoning map
Final report
Poster
Power point presentation
Metadata

## Slide 20: Conclusion
San Marcos and surrounding areas are rapidly growing
We will provide tools to help plan and enact regulations
We will deliver
  Interactive screening tool
  Updated airport hazard zoning map

## Slide 21: Questions?