## Slide 1: Construction of Geodatabase with Analysis of New Braunfels’ Drainage System
Project Proposal By Genius, Inc.

## Slide 2: Project Team Members
Scott Christensen
    Project Manager
Brad Dillashaw
    Assistant Project Manager
Sam Ortega
    GIS Analyst
Kelly McGauhey
    GIS Analyst
Jacqueline Carrillo
    GIS Analyst, Web Developer

## Slide 3: Summary
New Braunfels growth (10-year)
  14.6 sq. miles
  21,246 residents
Growth leads to new infrastructure needs
Several floods in recent years
  Broadway, 1998 and 2002
  June 9, 2010

## Slide 4: Broadway, 1998 & 2002
Broadway flood, 1998
Broadway flood, 2002

## Slide 5: June 9, 2010

## Slide 6: Purpose
Proposed geodatabase to help meet needs
  Centralized record-keeping
  Organized data
  Mapping capability
Will bring clarity and efficiency to financial and engineering decisions in the future
Detail geodatabase design and demonstration

## Slide 7: Scope
Primary Scope
  5 block area along W. San Antonio Street
  North extent: State Highway 46
  South extent: Santa Clara Road
Secondary Scope
  Time Permitting
  Expand study area meeting

## Slide 8: Walkthrough

## Slide 9: Walkthrough (cont.)

## Slide 10: Walkthrough (cont.)

## Slide 11: Scope Map

## Slide 12: Scope Purpose
Geodatabase
Manage Data
Collect Data
Use to Populate
Develop/
Explore
Test/Run

## Slide 13: Data
New Braunfels city data
  Street centerline
  City limits
  Building parcels
  Digital Elevation Model (DEM)
  Street Rating Score database
Pictometry & Remote Sensing Images

## Slide 14: Methodology
ArcGIS Database Design
  Feature classes:
    Sidewalks
    Crosswalks
    Curb & Gutter
    Ditches
    Storm Drains
  Attributes
    X-Y coordinate georeference
    Street Centerline georeference
    ‘Condition’
    Other attributes

## Slide 15: Methodology (cont.)
Data Input Design
  Street centerline reference
  Drop-down menus
  Didactic fields
  Notes field with image option
Data Collection
  Field data
  Remote imaging / pictometry
Database Population and Demonstration

## Slide 16: Budget
TASK | TOTAL HOURS | COST ($) | TOTAL COST ($)
Design Databases | 168 | 25 | 4,200
Data Collection | 100 | 20 | 2,000
Analyze Pictometry & Aerial Photography | 10 | 25 | 250
Populate Databases | 100 | 25 | 2,500
Finalize & Prepare Deliverables | 42 | 20 | 840
Project Management: Project Manager | 50 | 50 | 2,500
Project Management: Assistant Project Manager | 30 | 40 | 1,200
Equipment Cost |  |  | 2,406
Software Cost |  |  | 5,328
Travel Cost |  |  | 73
TOTAL COST |  |  | $21,297

## Slide 17: Timeline
TASKS | WEEKS |  |  |  |  |  |  |  |  |  | 
 | 2/20 – 2/24 | 2/27 – 3/2 | 3/5 – 3/9 | 3/12 – 3/16 | 3/19 – 3/23 | 3/26 – 3/30 | 4/2 - 4/6 | 4/9 – 4/13 | 4/16 – 4/20 | 4/23 – 4/27 | 4/30 – 5/4
Proposal | X |  |  |  |  |  |  |  |  |  | 
Data Collection |  |  |  |  | X | X | X | X | X |  | 
Analyze Pictometry |  |  |  |  |  | X |  |  |  |  | 
Progress Report |  |  |  |  |  |  | X |  |  |  | 
Design Databases | X | X | X | X |  |  |  |  |  |  | 
Populate Databases |  |  |  |  | X | X | X | X | X |  | 
Finalize & Prepare Deliverables |  |  |  |  |  |  |  |  |  | X | 
Presentation |  |  |  |  |  |  |  |  |  |  | X

## Slide 18: Deliverables
File geodatabase
  ArcGIS database
  Data input form
  Instruction manual
Final report
Poster
Website
Comprehensive CD
  All data and metadata
  Electronic copies of all deliverables

## Slide 19: Purpose of Website

## Slide 20: Conclusion
Project Results
  Initial creation and structure of geodatabase
  Populate and demo geodatabase
Implications
  Develop and add to database
  Identify and record future drainage issues
  Analysis of future drainage infrastructure needs

## Slide 21: Questions?
Point of contact: Brad Dillashaw, bd1197@txstate.edu