## Slide 1: Progress Report
Project Manager-Clancy Taylor
GIS Analyst/Web Designer-Will Johnston
GIS/Remote Sensing Analyst-Michael Amaral
GIS/Remote Sensing Analyst-Megan Branam

## Slide 2: Introduction
Austin, Texas
NeighborWoods Tree Planting Program
Mitigation of Urban Heat Island Effect
Effectiveness of Program

## Slide 3: Summary
Analyze the efficacy of NeighborWoods Program in mitigating UHI
  2002-2014
  Using surface temperature data (LANDSAT images)
Use point data about trees planted during program
Create a website that lays out final deliverables

## Slide 4: Tasks
Convert remote sensing images from USGS TIFF files for usage in ArcMap
Analyze surface temps & locations to NeighborWoods trees in ArcMap to visually analyze changes in temp and land cover
Provide statistical analysis of the significance of the effect of NeighborWoods trees on surface temp.
    Then quantify energy savings created by the NeighborWoods trees

## Slide 5: Work Completed
3 out of the 4 LANDSAT images are manipulated (4,5,7, still working on 8)
Base map created on ArcMap, ready for analysis

## Slide 6: Problems
Complexity of ERDAS Imagine
  Program producing different results with same inputs

## Slide 7: Work Scheduled
Finish converting LANDSAT 8 image into a surface temp image
Start work on GIS analysis
Web Design
Data interpretation and quality control
Prepare final copies of deliverables

## Slide 8: Updated Timeline
Sun | Mon | Tues | Wed | Thurs | Fri | Sat
29 | 30 | 31 | 1 | 2 | 3 | 4
5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 13 | 14 | 15 | 16 | 17 | 18
19 | 20 | 21 | 22 | 23 | 24 | 25
26 | 27 | 28 | 29 | 30 |  | 
Sun | Mon | Tues | Wed | Thurs | Fri | Sat
 |  |  |  |  | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30
31 |  |  |  |  |  | 
April
May
Data & Statistical Analysis
Data & Statistical Analysis
Web & Map Development
Web & Map Development
Data Interpretation & Quality Control
Data Interpretation & Quality Control
Final Deliverables
Presentation

## Slide 9: Conclusion
Because of difficulties, schedule has been updated and adjusted accordingly
  Original deadlines will still be met
Final deliverables will be complete May 4th
Final presentations held May 8th