## Slide 1
Geo-Tex Spatial
Solutions
Jennifer Zingery | Abel Avilez | Katie Kunz | Aya Udagawa
CONSULTANTS:

## Slide 2: Project Description
  Purpose: Creating interactive maps of watersheds for users of the GBRA website
  Scope: Watersheds that Guadalupe Blanco River Authority oversees

## Slide 3: Progress Overview
The project has been broken down into the following time periods:
  (1) Work Completed
  (2) Current Work
  (3) Future Work

## Slide 4: (1) Work Completed
Data Collection

## Slide 5: Work Completed (Continued)
Data Assembly
  Import Data into Arc-GIS
  Create Metadata
Revisions
  Revised Budget
  Revised Timeline

## Slide 6: (2) Work In-Progress
Data Assembly
  Making Map in Arc-GIS
Web Assembly
  Importing Arc-GIS Maps into Manifold

## Slide 8: (3) Future Work
Make Final Arc-GIS & Manifold Maps
Document Remaining Data (Metadata)
Creation of Web-Site (Sample Follows)
Prepare Final Deliverables
  Final Report, Presentation, CD
Present Final Report to GBRA (May 11, 2009)

## Slide 9
SAMPLE WEB SITE
HYPERLINK:
HOME PAGE
METHODOLOGY
PROJECT LIST
INTERACTIVE MAPS
- SOURCES
Future Work
(Continued)

## Slide 10: CONCLUSION
To Review:
  Project is on-time and on-budget
  Confident that data is best available
  Work is progressing smoothly
  Project will be delivered on schedule